## Sheet1
25 July 2009 - Eagle Court of Honor Preparation
Lead Time | Activity | Target Completion Date | Status | Notes
6 weeks prior
| Idenify Scouts to be recognized | 2009-06-13 | Complete | Eagle Scouts to be recognized: Timothy Hurst Evan Weaver Chris Gillespie
| Arrange for speaker |  | Complete | Colonel Phil Bossert - Professor of Air Force Science
5 weeks prior |  | 2009-06-20
| Request letters of appreciation |  | In-progress | letters requested from Congressman Ron Paul
| Identify other adult leaders who will attend &/or participate |  | Complete | Bill Gillespie, Eddie Zanner
4 weeks prior |  | 2009-06-27
Design program
Design invitations
Begin weekly announcements of Court of Honor via Troop e-mail
Schedule Minister to give Invocation & Benediction
3 weeks prior |  | 2009-07-04
| Identify all Scouts who will assist with ceremony |  |  | completion of this task may need to be delayed unto 11 July
2 weeks prior |  | 2009-07-11
Order cake from Cake Lady
Review & Check Program Script
Arrange for photographer
1 week prior |  | 2009-07-18
Bay Area HQ - Get Eagle pins from Bay Area Council HQ in Galvaston
Coordination - e-mail script to all participants who have a speaking part
Coordination - Master of Ceremonies to practice scipt
Other - Purchase gifts of appreciation for Scout Masters and Speaker
Scout Shop - Purchase eagle neckerchiefs & slides
Scout Shop - Purchase scout paper plates, cups & napkins at scout shop
With Scouts - Arrange to have rank log & candles
With Scouts - Arrange to have toop flag & stands
Day before COH
| Pick-up cake from Cake Lady | 2009-07-24
Purchase other refreshments - soft drinks
Day of COH |  | 2009-07-25
Set-up 2 hours prior to start-time
bring 4 extra copies of script
walk through script with MC
small table next to podium with water / cups
reserve font row of seats for new Eagles, the MC & all key speakers
set-up refreshments - ice for drinks